## Compliance Matrix
Business Win Now - SAMPLE Compliance Matrix - VA RFQ 36C26026Q1017 (Portland VA EMS SaaS)
Source: RFQ revised 10-13-2026 + Amendment 0001 (SAM.gov). Sample only; verify against the current solicitation.
Req ID | Section ref | Requirement | Response location | Owner | Status | Notes
ADM-01 | E.2.1.a | Submit signed, dated quote by email to CO Tyrone Whalen (tyrone.whalen@va.gov); copy Danielle Carrico per Amendment 0001 Q&A | Cover email | Capture lead | Open | ~10 MB/email limit; may split across emails
ADM-02 | SAM.gov notice / Amd 0001 | Quote due Nov 3, 2026, 5:00 PM Pacific (8:00 PM ET) | Cover email | Capture lead | Open | Amendment 0001 extended deadline from 10/13/2026
ADM-03 | E.2.1.b | Submit Parts I-III (required) as separate attachments; Part IV if past performance available | Submission package | Proposal mgr | Open | Formats/naming at contractor discretion (Amd 0001)
ADM-04 | SF1449 Blk 10 / Notice | 100% SDVOSB set-aside; NAICS 541519 | Part I | Contracts | Open | Verify SBA VetCert status; confirm in solicitation
P1-01 | E.2.b.i | Complete SF1449 incl. Block 17a (SAM UEI) and Blocks 30a-c | Part I | Contracts | Open
P1-02 | E.2.b.i / B.1 | Acknowledge all amendments (incl. Amendment 0001) | Part I | Contracts | Open
P1-03 | E.2.b.i / VAAR 852.219-75 | Complete VA Notice of Limitations on Subcontracting certificate | Part I | Contracts | Open | Offers without it not considered
P2-01 | E.2.b.ii / B.3 | Unit and extended prices for CLINs 0001-4001, two decimals, calculations correct | Part II | Pricing | Open | Options added to total for evaluation (E.4(b))
P2-02 | SOW travel / Amd 0001 | Include all travel and training costs in FFP line items; do not price optional modules/added licenses | Part II | Pricing | Open | Travel not separately reimbursed
P3-01 | E.2.b.iii Q1 | Fully operational COTS SaaS at award, no customization | Part III Q1 | Tech lead | Open
P3-02 | E.2.b.iii Q2 / Tech Reqs | FedRAMP-compliant, FedRAMP ID, hosted on FedRAMP-approved infrastructure | Part III Q2 | Tech lead | Open | Ready/In-Process acceptability not stated; confirm in solicitation
P3-03 | E.2.b.iii Q3 / Tech Reqs | Meets NIST 800-145 (SaaS) and NIST 800-53 Rev.3 | Part III Q3 | Security | Open
P3-04 | Tech Reqs | Registered in eMASS with current, approved VA ATO | Part III Q2-Q3 | Security | Open | ATO timing not specified; confirm in solicitation
P3-05 | E.2.b.iii Q4 | Multi-factor and replay-resistant authentication | Part III Q4 | Security | Open
P3-06 | E.2.b.iii Q5 | Data encrypted in transit and at rest | Part III Q5 | Security | Open
P3-07 | E.2.b.iii Q6 | Track loads, tonnage, deficiencies, labor types/costs, usage, assets (asset/part nos., manufacturer, model, location) | Part III Q6 | Tech lead | Open
P3-08 | E.2.b.iii Q7 | Configurable standard audit reports and ad-hoc user reports | Part III Q7 | Tech lead | Open
P3-09 | E.2.b.iii Q8 | Dashboards for performance metrics; historical data, analytics, trending | Part III Q8 | Tech lead | Open
P3-10 | E.2.b.iii Q9 / SOW 17 | Multi-level access (national/regional/local) with accurate role/permission mapping | Part III Q9 | Tech lead | Open | Be ready to demonstrate
P3-11 | E.2.b.iii Q10 / SOW 13 | On-site and web-based training before go-live; classroom instruction with proficiency evaluation | Part III Q10 | Training lead | Open
SOW-01 | SOW 17.4 | Single-tenant deployment; ability to run on virtual server on Government network | Part III Q2 | Tech lead | Open | See Amd 0001 Q&A
SOW-02 | SOW 10.1 | Licenses for 10 initial users; unlimited site licenses for Government-defined facilities | Part III / Part II | Pricing | Open | User count (10 vs ~20) - confirm in solicitation
SOW-03 | SOW Tier II | Tier II help desk via phone/email/chat, M-F 8 AM-6 PM Pacific | Part III | Support lead | Open | Delays >2 business days noted in past performance
SOW-04 | SOW 6.1 | System testing and acceptance plan within 5 days of award (3 phases) | Part III | PM | Open
SOW-05 | SOW Kickoff | Technical kickoff meeting within 10 days of award | Part III | PM | Open
SOW-06 | SOW data migration | Load up to 2 years of existing EMS records | Part III | Tech lead | Open
SOW-07 | SOW Emergency Ops | Disaster recovery, failover and backups; RTO/RPO set with VA POC | Part III | Security | Open
SOW-08 | SOW reporting | Progress/deliverable reports in Microsoft Word format | Part III | PM | Open
P4-01 | E.2.b.iv | Past performance (last 5 yrs): entity/address, services and scale, reference POC, dates, contract type and value | Part IV | Capture lead | Open | Users/sites may replace sq. ft.; CPARS accepted (Amd 0001)
EVAL-01 | E.4 (52.212-2) | Best value: Technical, Past Performance, Price; no alternate quotes | All parts | Proposal mgr | Info | Relative weights not stated - confirm in solicitation
INS-01 | Insurance clause | Evidence of general liability insurance before award | Pre-award | Contracts | Open | confirm in solicitation for limits